## Sheet1
Task# | Project Task | Due Date | Note
1 | Finalizing the Data Set | Sep 23rd
2 | Tidying up and transformation | Sep 30th | Data Profiling, transformation and Clean up mechanism: R Libraries (tidyr, dplyr, stringr etc.)
3 | Designing the SQL Database | Sep 30th | MySQL DB - Local instance for the project team; repository loaded in GitHub
4 | Prepare the DDL and Load Script | Sep 30th
5 | Get the Database Fully loaded and backed up | Sep 30th
6 | Exploratory Data Analysis | Oct 7th
7 | Visualization/Statistical Analysis | Oct 14th | R Libraries (ggplot2 etc.)
8 | Documentation - Markdown | Oct 14th
9 | Presentation - Powerpoint | Oct 21st | Oct 21st/Video Presentation Mockup - Rom to own stitching individual videos
Most Valued Data Science Skills - - Separate slide for skills - At the beginning or end - Sharing association of the skills during specific project tasks